## Sheet1
Week | Hours | Summary of the work
2024-05-13 | 15 | onboarding on testing, data preprocessing, project details, testing of 3 participants, recruitment in language and psychology faculty, pint of science, no stress bar, storgata camping and tromso public library
2024-05-20 | 17 and 20 minutes | testing of 2 participants, session 2 data reprocessing for participants 1. 10, 11, 3, 5, 6, 9, session 3 data reprocessing of participants 3, 5, 7, 8, 9, 10, 13, 14, 16, session 4 data reprocessing of participants 3, 5,7, onboarding and practice on Brainvision analyzer and onedrive, documentation of preprocessing progress across participants and sessions, pipeline building
2024-05-27 | 13 hours and 20 minutes | building pipeline in sessions 2 and 3. communicating with brainvision customer support and editing/repairing damaged files, ICA for session 3 participants 7,8,9,16, ICA for session 2 participants 1, 10, 11, 2, 3, 5,6,7,9, research and review of educational materials on iCA, artifact removal, segmentation, marker editing etc
2024-06-03 |  | read Pereira Soares paper, set up github account and application, set up teams, read up on artifact rejection, tried to adjust segmentation on session 3, tutorial on Github use, segmentation, and troubleshooting with Pablo
2024-06-10
2024-06-17
2024-06-24
2024-07-01
2024-07-08
2024-07-15
2024-07-22
2024-07-29
2024-08-05
2024-08-12
2024-08-19
2024-08-26
2024-09-02
2024-09-09
2024-09-16
2024-09-23
2024-09-30
2024-10-07